## Sheet1
| FY21 | Q3 |  |  | Q4 |  |  | FY22 | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | FY23 | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Apr | May | June | Jul | Aug | Sept |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep
Order Management System |  | Develop electronics capture of routine and emergency orders |  |  | Develop/setup interface to push order from eLMIS to the WMS
|  |  | Test the electronic capture of orders |  |  |  | Test the interface to push order in WMS
Identify and Fix bugs
Implement electronic capture and train facilities
Master Data Management | [5 empty] | Develop the synchronization mechanism of the facilities Catalog between eLMIS,National HMIS and WMS |  |  | Q1 Oct: Deploy or develop a UI portal for the facilities catalog; Q1 Dec: Develop the synchronization mechanism of the products Catalog between eLMIS and WMS; Q2 Feb: Deploy or develop a UI portal for the product catalog; Q3 Apr: Develop the synchronization mechanism of the Providers Catalog between FHIR and WMS; Q3 May: Deploy or develop a UI portal for the suppliers catalog
[10 empty] | Test and correct bugs in the facilities catalog |  |  |  | Test and correct bugs in the products catalog |  |  | Test and correct bugs in the Suppliers catalog
Add the GS1 coding in the products list in the Product catalog
[10 empty] | Train users and administrators on the facilities catalog |  |  |  | Train users and administrators on the product catalogs |  |  | Train users and administrators on the Supplier catalogs
Warehouse Management System | [8 empty] | Q1 Oct: Integrate the module to generate and print the label through the WMS
[10 empty] | Aquire equipments such as Barcode scanners, Label printers |  | Test the new equipment with the new printer module
Test the scanning and the identification of products for counting, picking and distribution using GS1 coding
Supplier & Contract Mgmt System
[16 empty] | Document the Software Specifications for the contract Management |  | Develop the Contract Management Module in SAGE
Test the Contract Management Module
[22 empty] | Create extension for Contract and related transactional data in FHIR | Develop the Synchronization mechanisme of the contract between FHIR and WMS |  | Develop a supplier performance analysis dashboard on PowerBi using contract FHIR endpoint datasource