## NPC Implementation Plan
# | Activity | Activity Owner | Dependency | Deliverables | Primary Resources* |  |  | 2020
[5 empty] | HQ | PSM FO | GoM | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Product Data and Process Management
1 | Document draft Product Master Data Management SOPs |  |  |  | Swaroop | TBD | TBD | bar: 2020 Oct
2 | Review, revise and approve Product Master Data Management SOP |  | Activity 7 |  | Swaroop | TBD | TBD | 2020 Oct: ✓; 2020 Nov: WIP
3 | Collect Product Master Data from Central Medical Stores and other Entities |  |  |  | Swaroop | VR | TBD | bar: 2020 Jun to 2020 Oct
4 | Define simplified list of GS1 aligned product attributes |  |  | GS1 based Item Master attribute list | Sean | VR | TBD | bar: 2020 Mar to 2020 May
5 | Send Master Data request letters to Donors |  |  | Draft letter shared with MOH | Swaroop | TBD | TBD | 2020 Nov: WIP
6 | Collect GS1 item master data from PSM and other donors (& from physical packages) |  | Activity 11 | GTINs & GS1 Item Master Data | Swaroop | VR |  | 2020 Nov: WIP
7 | Map Existing Product Identifiers to GTINs where available (from PSM, GFPVAN etc.) |  | Activity 12 |  | Sean | VR | TBD | 2020 Jul: ✓; 2020 Aug: ✓; 2020 Sep: ✓; 2020 Oct: ✓; 2020 Nov: WIP
8 | Finalize list of data attributes, for configuration in NPC, based on harmonized data |  | Activity 9, 10 |  | Sean | VR | TBD | bar: 2020 Jul to 2020 Sep
9 | Review harmonized data with key stakeholders |  | Activity 13, 14 |  | Swaroop | VR | TBD | bar: 2020 Nov to 2020 Dec
10 | Assign relevant product classifications |  | Product Master Data Harmonization | Reviewed & Analyzed Product Master Data | Swaroop | TBD | TBD | bar: 2020 Dec
11 | Install and use PCMT to organize product data (in the interim) |  |  |  | Sean | VR | TBD | bar: 2020 Jun
12 | Ongoing data management support |  |  |  |  | TBD | TBD | bar: 2020 Dec
People Management
13 | Setup Master Data Governance Group |  |  |  | Swaroop | TBD | TBD | bar: 2020 Dec
14 | Establish & Assign Catalog Manager Role |  |  |  | Swaroop | TBD | TBD | bar: 2020 Nov to 2020 Dec
15 | Identify Technical Resource to manage NPC System Administration |  |  |  | Swaroop | TBD | TBD | bar: 2020 Dec
Tool Procurement
16 | Select/Decide on a software tool for NPC |  |  |  | Swaroop | TBD | TBD | bar: 2020 Aug to 2020 Sep
17 | Define NPC system requirements |  |  | NPC System Requirements | Swaroop | TBD | TBD | bar: 2020 Apr
18 | Select tool & vendor for NPC implementation |  | Activity 4 |  | Swaroop | TBD | TBD | bar: 2020 Jul
19 | Finalize Scope of Work NPC tool implementation |  | Activity 5 | NPC Implementation SOW | Swaroop | TBD | TBD | bar: 2020 Jul
20 | Tool Implementation
21 | Develop detailed project plan for implementation |  |  |  | Swaroop | VR | TBD | bar: 2020 Jun to 2020 Jul
22 | Develop NPC design specifications |  | Tool & Vendor Selection | NPC Design Specifications | Swaroop | VR | TBD | bar: 2020 Jul to 2020 Aug
23 | Define integration specifications to integrate with other systems for data exchange |  | NPC Design | `-NPC Integration Plan & Specifications (with enhancement details for other Systems) | Swaroop | VR | TBD
24 | Develop a change management plan |  | Activity 20, 21 | Change Management Plan | Swaroop | VR | TBD
25 | Configure & develop NPC (including testing support such as bug fixes) |  | NPC Design | NPC Tool (Available for Testing) | Swaroop | VR | TBD | bar: 2020 Sep to 2020 Dec
26 | Product Master Data Migration into Test Instance |  | NPC Development |  | Swaroop | VR | TBD | bar: 2020 Sep to 2020 Nov
27 | Testing (System, Integration & User Acceptance) |  | NPC Development | NPC Testing Reports | Swaroop | VR | TBD | bar: 2020 Nov to 2020 Dec
28 | Migrate Product Master Data into NPC Production Instance |  | Testing Completion |  | Swaroop | VR | TBD | bar: 2020 Dec
29 | Configure & Deploy NPC Mobile App |  |  |  | Swaroop |  |  | 2020 Nov: WIP
30 | User Training |  | Testing Completion | User Training Documents | Swaroop | VR | TBD | bar: 2020 Dec
31 | NPC Roll Out |  | Testing Completion & User Training | NPC Operational | Swaroop | VR | TBD | bar: 2020 Dec
32 | Ongoing system admin support |  | NPC Roll Out |  |  | VR | TBD | bar: 2020 Dec
*Primary Resources will help with activity coordination, oversight, reviews and execution depending on the activity