## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 3: Data Collection Timeline
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Data Collection Timeline
  Learning Objectives
  Have a more detailed picture of the data collection phase, and the importance of advance planning:
  Three main data collection activities
  Advance planning
  Data collection components
  Operations structure

## Slide 3: Data Collection Preparation & Actual Data Collection
  Data Collection Preparation usually occurs during the 3rd “and” “or” through the 12th week post project initiation.
  Data Collection encompasses preparing for three major activities:
  Desk review activity
  Stakeholder workshop/supply chain mapping
  Field data collection efforts
Notes: Objective: Have a more detailed picture of the data collection phase, & importance of advance planning
More detail on data collection period
Important milestones
Objective: Be able to recruit appropriate date collectors in a timely way
recruiting policy, compensation, restrictions, etc.
Setup operations structure
Setup practice site

## Slide 4: Overview of NSCA 2.0 Timeline
Notes: You will recall this slide from earlier. Although the data collection preparation is shown here corresponding to the month before actual field work, some of the activities will take place throughout the planning stage as well.

## Slide 5
Notes: Week 13 and 14 activities are part of the data collection stage, before that is the data collection preparation stage.

## Slide 6: Advance Planning
Request advance information on supply chain landscape, context, tracer lists and other supply chain mapping requirements.
Request advance information on data – eLMIS or LMIS data extraction and management.
Identify what levels of service in the supply chain store LMIS/eLMIS data and who has access very early.
For stakeholder workshop – decide whether or not to gather most of the required information remotely (to draft a supply chain map) or to hold a workshop early on as opposed to at the start of field work.
Notes: You should know at what levels data collection is paper based and what levels are electronic. Try to get access to eLMIS data ahead of time to familiarize yourself with the structure. The two proposed times for the stakeholder workshop—depends on how much input you need for planning and if the steering committee is enough or if it needs to be the full set of stakeholders. This is often dependent on the different operating cultures of the country.

## Slide 7: Data Collection Components - I
  Desk review activity
    Review documents: supply chain strategy, supply chain implementation plan, previous assessments or audits, etc.
    Review data: gain access to eLMIS/LMIS data ahead of time
    Timeline:
      Thorough review prior to field work (part of planning/data preparation stages)—several weeks
      Refer to these documents again when writing the report
Notes: The desk review should be done in advance. It should really start during the planning stage and not waiting for the data collection preparation stages. In addition to reviewing documents to familiarize yourself with the supply chain system in country, the team should also gain access and review the eLMIS/LMIS data. It will help the team understand what is and what is not in the system so that the requests for specific data items will be more informed.

## Slide 8: Data Collection Components - II
  Stakeholder workshop/supply chain mapping
    Supply Chain Mapping
      Prior to workshop: assessment team should familiarize themselves with existing supply chain maps
      During workshop: agreement on the map (and levels to be included in the assessment)
    Tracer Commodities
      Prior to workshop: Request list from MOH (Chief Pharmacist), review and have proposal for cutting down
      During workshop: Have participants weigh in on the list and agree on which to remove/add
Notes: Including the supply chain mapping as part of the stakeholder workshop is a good way to get everyone involved in the assessment and ensure buy in. However, keep in mind that the number of parallel supply chains, levels of the system, etc. need to be decided ahead of time because that determines, the scope, sampling, timing, and budget. Only minor changes should be made at this stage. If you feel there will be a lot of debate this needs to happen far in advance of the field work. The problem is usually people want too many tracer commodities. Go into the stakeholder meeting with a proposed list (slightly longer than you want) and ask participants to help narrow this down. This needs to be resolved soon after the workshop in order to program SurveyCTO and print hard copies. Again if you feel this will be contentious it may need to be handled in a separate meeting in advance of the field work.

## Slide 9: Data Collection Components - III
  Field Data Collection Efforts
    Timing
        Immediately after training (1 week for training)
        2-4 weeks data collection
    Considerations
        Schedule interviews with MOH/ Regulatory Authority/CMS in advance
        Allow time for return visits
        Try to collect everything during the 2-4 week data collection period
Notes: Advance planning is key for the central level data collection! Often times you will need to go back for a follow up meeting if you cannot meet with everyone. Trying to follow up after the implementers have left the country is nearly impossible. Start at the beginning of the data collection period to allow time for this. If the central team finished early they can join a field team or start preparing debriefs, etc.

## Slide 10: Operations Structure for Field Data Collection
    Data management team
        -Located in the capital, led by data manager
        -Respond to questions from the field
        -Update SurveyCTO form if needed
        -Review data coming in
    Central data collection team(s)
        -Conduct central level CMM and KPI data collection, led by assessment manager
    -MOH, regulatory authority, CMS (may be multiple warehouses)
    Facility data collection teams
  -Courtesy calls to Provincial and/or District health office
  -Regional warehouse, facility (hospital, health center, health clinic) CMM and KPI data collection
Notes: During the active 2-4 weeks of data collection there are three main teams conducting the data collection: the central and field data collection teams and the data management team that oversees all data review and troubleshoots the SurveyCTO form and reviews the data coming in. The Project lead will also remain at the central level assisting with the central data collection and troubleshooting overarching problems. The Project Lead will also prepare the debriefs.