## Slide 1: NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA 2.0) STAKEHOLDER TRAINING
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order
Day 3: Kick-Off Exercise

## Slide 2: NSCA 2.0 Exercise I
In small groups please prepare:
Key task lists to implement an NSCA
Plot those tasks against a timeline
Estimate the types and quantities of resources you will need
Use those resources to prepare a draft of budget line items
Group 1s :–
Focus on tasks A & B and be ready to report back.
Give a few minutes thought to C & D to comment on Group 2’s presentation
Group 2s :–
Focus on tasks C & D and be ready to report back.
Give a few minutes thought to A & B to comment on Group 2’s presentation
30 minutes
Notes: This first exercise of the day is something of an ice-breaker to get the mental juices flowing, and to get the trainees thinking about what is needed to run a successful NSCA assessment. The goal is to apply the tasks listed and discussed at a high level yesterday to a timeline, and to consider the resources (human, physical and financial) needed for an assessment.
For this exercise, think about what size country you plan on implementing and the scope of the assessment you plan on assessing. Some key pieces of the timeline you will want to think about are gaining stakeholder buy-in and investment, supply chain mapping and validation, training of data collectors, data collection.
Numbers of groups, and group size will depend on the number of trainees, always aim for a minimum of two groups to get contrasting answers, and if possible keep the numbers of groups even. Ideal size is 4-6 person per group. Obviously if you have more than 2 groups then split the questions two sets of groups, i.e. if you have six groups then ask groups 1, 3 & 5 to answer the questions under group 1 in the slide, and groups 2, 4 & 6 to answer the Group 2 questions. Feel free to amend the slide accordingly.
NB for presenters: This will exercise test some of the learning from Day 1, and should draw out some possibly wide divergences of view of time and cost in particular, and this is good because to emphasizes the point that there is no right answer, and ever NSAC implementation is different to one degree or another.

## Slide 3: Sample timeline items
Scoping the project
Preparing international travel (if applicable)
Plan and prepare the assessment
Stakeholder mapping workshop
Training data collectors
Data collection in the field
Dissemination

## Slide 4: Sample timeline

## Slide 5: Budget items
Human resources – consultancies, staff LOE, per diems, etc
Travel, lodging and logistics
Training costs
Workshop costs
Technical equipment and software costs
Communication costs
Miscellaneous expenses
Number of sites assessed
  Increases the days of data collection / number of data collectors needed
  Increases transportation costs
Assessment team size and salaries
  8-12 full time assessment team members
  (Don’t forget scoping, data analysis, and dissemination time!)
International staff
Country size and transportation means
Some key cost drivers

## Slide 6: Budget Estimates
The budget to implement a NSCA assessment will largely be dependent upon a number of factors, including scope, size, makeup and design of the assessment team, etc.
An estimate cost range for three types of NSCA:
Snapshot NSCA: For a small or snapshot NSCA that uses a significantly smaller sample size that is not nationally representative, estimate $50,000 to $100,000 budget.
Targeted NSCA: For a targeted medium size NSCA that focuses on either one level of the supply chain, or a few technical modules across the supply chain, or may intend to simply provide decision-makers with information about a certain systemic challenge, consider a budget of $100,000-$200,000.
Full-scale NSCA: For a full-scale NSCA which requires a sizable random sample across all levels of the supply chain, is nationally representative within certain confidence interval, estimates can run from $350,000 to $500,000.

## Slide 7: Be sure to consider
Size of country
Scope of NSCA – snapshot, targeted, or full; number of health facility levels; other disaggregation
Size of assessment team and number of enumerators needed
Resources needed – human, physical, technical, financial, etc.
Timeline – from gaining stakeholder buy in all the way through to dissemination