## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 3: Work Planning and Project Management
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Work Planning and Project Management
  Learning Objectives
  To understand what is required in planning and managing an NSCA:
  Developing an NSCA workplan
  How to estimate overarching timeframes required to plan and execute an NSCA
  How to set realistic, pragmatic milestones and key decision points
  Assessment teams and roles
  Budget planning and implications

## Slide 3: Overview of NSCA 2.0 Timeline
Notes: Finalize scope for the NSCA triggers development of workplan and budget. Detailed workplan must align with overarching phases and their time estimates. In looking at the timeline you can see that data collection is only 3-5 weeks of a 6+ month project, example in a few slides shows a 9-month process. In general we are aiming for 6-9 months. NSCA 1.0 was 12-18 months in some cases.
Draw up overarching timeframe schema by laying out key activities and general time estimates.
Estimates encompass the following:
Project start date.
Field Collection Start date.
Time within Project phases

## Slide 4: Estimating Timelines
Consider the four major phases of an assessment:
1. Planning and Preparatory phase (estimated ~ 12 weeks)
II. Data Collector Training/In-country Assessment (estimated 3 ~ 5 weeks)
Data Analysis and Interpretation (estimated 4-6 weeks)
Reporting and dissemination (~ +4 weeks up to initial draft of report depending on reviews)
Summarize workplan requirements per phase in terms of activities and outputs.
May be helpful to use a Gannt chart or other planning tool to visualize the workplan
Tool kit planning tools: Gannt chart, Daily Activity schedule and Country Planning Checklists
Notes: The Daily activity schedule is included in a subsequent session.

## Slide 5: Key Milestones and Decision Points
Notes: To Presenter: 1. Final scope triggers development of workplan and budget. Detailed workplan must align with overarching phases and their time estimates.
2. Summarize requirements per phase in terms of activities and outputs.
3. May be helpful to use a Gannt chart or other planning tool to visualize the workplan.
As with any project we all know that the report finalization can take a long time if deadlines are not set and met for the reviews and revisions. The longer this drags out the less relevant the findings.

## Slide 6: Key Milestones and Decision Points
Planning ~ 3 weeks
Milestone start: Validation of assessment, establishment of assessment objectives and secured commitment to conduct assessment
Milestone end: Agreed upon expectations in terms of scope and supply chain facility types to be assessed
Notes: To Presenter: 1. Mention examples of assessment objectives.
2. Secured commitment to conduct assessment is validating that key documents are in place: 1, SOW or TOR 2. Confirmed funding 3. Information assessment requestor 4, Information on participating institutions.
3. Mention examples of scoping requirements to be defined.
4. Mention all the other milestones for planning and preparation and timelines.
The scope (including facility types/levels of the supply chain and functional areas) determines (or is determined by) the funding.

## Slide 7: Key Milestones and Decision Points
Preparation and Project Management~ 9 weeks
Milestone start: Agreed upon scope
Milestone intermediary I: Stakeholder engagement/communication and coordination
Milestone intermediary II (data collection preparations): Constitute project team
Milestone intermediary III: Finalize assessment workplan and budget
Milestone intermediary IV (data collection preparations): Identify facility list and sample sizes
Milestone end: Inform facilities to be visited and complete pre-visit preparatory work
Notes: To Presenter: 1. Mention examples of assessment objectives.
Ensure stakeholders are informed and able to participate as needed. Next sessions specifically focuses on stakeholders.
Planning (3 weeks) and Preparation (9 weeks) make up the 12 weeks.
Plan logistics for data collection.

## Slide 8: Key Milestones and Decision Points
Data Collection ~ 3-5 weeks
Milestone start: Gather preliminary information through desk review
Milestone intermediary I: Stakeholder workshop/supply chain mapping conducted
Milestone intermediary II: Data collection teams trained and deployed
Milestone intermediary III: Collect CMM and KPI Data
Milestone end: Daily data uploaded from tablets to central database
Notes: To Presenter 1. Discuss each data collection and analysis milestone.
Finalize scope for the NSCA triggers development of workplan and budget. Detailed workplan must align with overarching phases and their time estimates.
Draw up overarching timeframe schema by laying out key activities and general time estimates.
Estimates encompass the following:
Project start date.
Field Collection Start date.
Time within Project phases
Although supply chain mapping takes place during the data collection phase, an understanding of the supply chain needs to happen during the planning phase as the scope and sample are determined.

## Slide 9: Key Milestones and Decision Points
Data Analysis ~ 4-6 weeks
Milestone start: Data Cleaned and Compiled
Milestone end: Generated CMM and KPI analysis outputs and summaries
Synthesis and Report Development ~ 5-7 weeks
Milestone start: Shared results with core assessment team
Milestone end: Interpreted findings
Notes: These are occurring simultaneously.

## Slide 10: Key Milestones and Decision Points
Report, Review and Revision ~ 4-8 weeks
Milestone start: Agreed upon findings by stakeholders
Milestone intermediary I: Iterative report review
Milestone end: Report Dissemination
Notes: As mentioned previously, the more rounds of review the longer it takes to finalize the report. Need to establish and stick to deadlines. Report dissemination may include dissemination event.

## Slide 11: Teams and Roles
Team and Roles:
There are five teams necessary to conduct an NSCA:
Governance Team
Steering Committee
Core Assessment Team
Data Collection and Analysis Team
Data Collectors
Notes: The definition of these five teams are covered in the next few slides. These are one version of teams as laid out in the Implementation Guide. The data collectors are really a sub-team within the Data Collection and Analysis Team. Don’t worry as much about what the teams and individuals are called, but focus on the activities that need to get done.

## Slide 12: Governance Team
Governance Team is needed to provide high level leadership, oversight and decision making
Usually includes one high-level official from key stakeholder organizations with budget and resource authority
The Governance team will not be involved in day to day operations
The Governance team encompasses key stakeholders such as:
  Ministry of Health
  Technical assistance partner (if any)
  Donor or other relevant international partners
The constitution of this team depends on the local situation and needs
Notes: Governance team need to be kept updated on progress, to approve changes to scope/roles, and they can also direct resources in-country to support assessment activities. Donor only if donor funded.

## Slide 13: Steering Committee
The SC oversees the activities of the core team. (Some members of the Steering Committee (SC) may also be part of the core team)
Includes members critical to the assessment and regularly involved in the operations.
The members of the steering committee are usually involved in specific management and/or technical activities.
Receives regular updates from Project Lead.
The Steering Committee encompasses:
  One high ranking MOH official
  TA partner (if any)
  Any other persons determined by the Governance Team
Notes: The Steering Committee complements the Core Assessment Team. Providing periodic support.
The Steering Committee should work closely with the Project Lead to facilitate decision making, speed implementation and approvals.
Key agenda items of first SC meeting include but not limited to: assessment objectives; scope; process and expectations.
SC needs to be aligned with updates to SOW.

## Slide 14: Core Assessment Team
Core Assessment Team is led by the Project Lead, who establishes all teams and is responsible for coordinating tasks across all teams.
The core assessment team is responsible for executing the assessment
The Core Assessment team encompasses:
Project Lead: Focal person, liasion between stakeholders
Assessment Manager: Senior Manager with supply chain expertise
Data Manager: Statistician and Data manager
Logistics Coordinator: POC for service providers (for training and field work)
Notes: To Presenter: Core Assessment team roles: Project Lead–Liasion between stakeholders (i.e. MOH, District Officials, IPs, etc.)—therefore a local
Assessment Manager – A senior manager with supply chain expertise, can be from the IP
Data Manager –A proficient Statistician/Data analyst capable of designing the analysis plan, assessing data quality, collating and analyzing the data collected
Logistics Coordinator: POC for service providers (e.g. scheduling drivers, vehicle rentals, lodging, printing, training venue (booking, meals & refreshments), buying airtime, phones, tablets, etc.

## Slide 15: Data Collection and Analysis Team
Data Collection and Analysis team is responsible for all in-country data collection and analysis activities to gather and analyze CMM and KPI data.
Preferable to use current supply chain actors as data collectors
Each health facility team should include 2 – 4 people depending on the size of the health facility, while central level facility should include one or more teams of up to 4 people
The Data Collection and Analysis team encompasses:
  Assessment Manager
  Data Manager
  Data Collection Supervisors
  Data Collectors
Notes: The size and total number of data collectors will depend on the assessment scope, time frame, volume of data being collected, sample size, budget, and HR capacity. Although preferable to use current SC actors, need to balance this with not having someone collect data for something they are responsible for. For example, in Zambia we use the Provincial Pharmacists as the data collection team leads. They were not allowed to go to the Province they manage or where they are from.

## Slide 16: Day II: Resource and Skill Requirements
Team Member/Role | Role | Team/Group | Resource level
Project Lead | Project lead for the overall execution of the NSCA Liaison with stakeholders (MOH, donors, etc.) Leads writing activities | Core assessment Team, Steering Committee, Data Collection Team (oversight) | Project Management (50-100%)
Assessment Manager | Focal person for the assessment operations Leads/coordinates all assessment activities in liaison with partner and steering committee Leads data collection at the central level | Core assessment Team, Steering Committee, Data Collection Team (central level) | 100% time throughout the assessment
Data Manager | Sampling, Analysis Plan, Analyzes Data, Advanced statistical analyses, Data Quality Checks Key role in analysis and interpretation activities | Core assessment Team, Steering Committee | 100% time throughout the assessment
Logistics Coordinator | Logistics for training and field work | Core assessment team | 100% time during training week and throughout data collection. 50% in build-up to data collection.
Data Collection Supervisor | Supervises data collectors and oversees data collection activities in the field | Data Collection Team | 100% time during training week and throughout data collection. 50% in build-up to data collection.
Data Collector | Conducts site visits to collect assessment data | Data collection team | Data Collection 100% time during training week and throughout data collection)

## Slide 17: Budget Planning and Implications
Running budget scenarios based on different data collection team sizes, level of effort and number of field data collections is a useful process to reach a realistic and reasonable budget
Summarize requirements per phase in terms of activities and outputs
Important to consult MOH, donors, TA partner and relevant local stakeholders throughout the entire budgeting process
Notes: To Presenter: 1. Running budget scenarios based on different data collection team sizes and level of effort will help.
2. Summarize requirements per phase in terms of activities and outputs.
3. May be helpful to use a Gannt chart or other planning tool to visualize the workplan.
If you plan to visit 100 health facilities, one team could take up to 100 days, which is not feasible. 10 teams could do it in 10 days, depending on distances between facilities.
Note that we are covering budgetting here at the end of this session, but you saw that it is included in the project initiation phase and finalized in the planning phase.

## Slide 18
Notes: The point is not to go through this line by line, but mention that the tool kit has these sample budget templates. Reminder of morning session and cost drivers. Point out how little the SurveyCTO license is out of these budgets if this is an issue.