## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 3: Scoping and Customizing
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Scoping and Customizing
  Learning Objectives
  To understand scoping variables and how and when decisions on scope impact implementation:
    Scoping variables
    Timing for finalizing and updating scope
    Impact of scoping on implementation
    Customization—do’s and don'ts

## Slide 3: Scoping an Assessment
  Commences when assessment objectives are set
  Builds on initial scope of work developed prior to planning phase detailing:
    Type of assessment comprehensive (full) or targeted
    Targeted may be functional or geographical or focused on administrative entities or levels of service provision
    Implementation timelines
    Expected outputs
    Stakeholder roles and responsibilities
  Factors influencing scope: human resources, timeline, and available budget.
Notes: Functional: All or subset of 11 functional modules
Geographical: Parts of the country
Administrative entities: one of several parallel SCs
Levels of the SC
The work should dictate the timeline, but you may have a deadline by when this needs to be completed

## Slide 4: Scoping Variables
  These have to be clearly defined:
  Regions- National, State, district, health facility or pharmacy stores.
  Supply Chain functional areas- e.g. Warehousing etc.
  Service Delivery Levels and Types- Tertiary (Comprehensive), Secondary or Primary or Private.
  All Core KPIs must be included in line with scope.
  Select Optional KPIs should be considered.
  List of tracer commodities for calculating KPIs.
  Sample size as defined in sampling frame.
Notes: As discussed on day 2 the optional KPIs can provide more information, but each additional KPI requires time to collect. Need to determine if the data required is easily available. The more tracer commodities, the longer at each storeroom. For the regional breakdown this just indicates what is included, but not that it is representative at these levels. Sample size depends on size of country, CI, MOE desired (covered under sampling section).

## Slide 5: Timing for Scoping Decisions
  Timing and Implications of defining and updating scope
  Preferable to start early in the planning and prep phase.
  Early definition of scope makes it easy to define resource requirements, sample size, detailed workplan, agree on time lines and budgeting.
Notes: Resource requirements include financial and human resources.

## Slide 6: Scoping Impact on Implementation- Definition of sampling approach and sample size
  The sampling approach must balance the need for holistic and representative data against the budget constraints, and the opportunity costs (e.g., the degree to which normal work patterns may be disrupted by the assessment).
  The size of the sample is determined depending on the agreed scope of the assessment (i.e. what programs and levels of the supply chain will be included in the assessment) and using an appropriate rationale and method.
Notes: Does the sample need to be nationally representative? Can it be a smaller sample or convenience sample?

## Slide 7: Scoping Impact on Implementation- Number of data collectors
  The total number of data collectors and number of data collection teams depend on the assessment scope, time frame, volume of data being collected, and sample size, as well as available budget and other resources and related constraints (e.g. shortage of HR).
  Other elements that inform the number of data collectors include:
  Types of Supply Chain Levels.
  Size of facility within sample.
  Physical distances between sites.
  Time required or available to complete data collection at all sites.
Notes: For example, for 100 facilities, one data collection team would take ~100 days! The more tracer commodities, the longer collecting the KPIs and the longer at the central warehouse! Physical distances between sites, but also terrain. How many facilities can you cover in a day? Assume 1 with time to get near the second.

## Slide 8: Scoping Impact on Implementation- Training and Tool/Material Updates
  The NSCA 2.0 data collection training content and related materials need to be refined or customized to local context or needs and the following:
  The right language and terms are used for the country being assessed.
  The right functional domains are covered for the levels of the SC system being assessed.
  The correct designations of staff to be interviewed at facilities in the site-visit sample are identified.
  The list of tracer commodities.
  Any additional relevant specific considerations for the context (e.g. MOH/organizational norms, protocol, code of conduct, etiquette, procedures, processes, standards, etc.) to be mindful of during preparations and execution of the assessment.
Notes: Language and terms: Province, State, County, etc.
MOH/organizational norms: for example, do you need to make a courtesy call to the CHT before going to the DHT, etc.

## Slide 9: Scoping Impact on Implementation- Appropriateness of tracer commodity list--I
  Based on the objectives and scope of the assessment, a list of tracer commodities is developed for use in measuring KPIs
  Stakeholders will review and finalize the list of tracer commodities at the stakeholders/supply chain mapping workshop
  Important to also include stakeholders and products from "vertical" (i.e., separate) supply chains that might store commodities in different locations if these vertical supply chains are included in the scope of the assessment
  Tracer commodities should have been available in country for the previous 12 months (i.e. not a newly introduced commodity)
Notes: While the implementers of the assessment could include as many tracer commodities as they would like, they should be mindful that adding more than 11 or 12 will slow down data collection could impact the ability of the team to finish data collection at larger sites in one day. Need to balance interest of many health programs. Probably a better way to assess the introduction of a new commodity than including it in the NSCA. Will adding a commodity require you to add another type of facility—e.g. in Zambia we did not add TB commodities or vaccines so did not need to go to the Provincial store rooms. LLINs may be stored in a separate warehouse.

## Slide 10: Scoping Impact on Implementation- Appropriateness of tracer commodity list--II
Tracer commodities should generally reflect a good mix of both major program specific drugs, some essential drugs that may not necessarily be considered "priority program drugs“, other important non-program products, and also key commodities that significantly impact the budget/expenditure.
The number of tracer commodities may vary, depending on what local stakeholders consider appropriate to the disease patterns, health system, disease programs, and patient demand.
8 -12 tracer commodities is recommended
Notes: While the implementers of the assessment could include as many tracer commodities as they would like, they should be mindful that adding more than 11 or 12 will slow down data collection could impact the ability of the team to finish data collection at larger sites in one day.
Tracer commodities should generally reflect a good mix of both major program specific drugs (e.g., ARVs, ACTs, rapid diagnostic kits, contraceptives), some essential drugs that may not necessarily be considered "priority program drugs" (e.g., critical antibiotics, MCH drugs), other important non-program products (e.g, antibiotics, oral rehydration solution (ORS)), and also key commodities that significantly impact the budget/expenditure (e.g., high cost/unit products, high turnover resulting in overall high total budget, etc.)

## Slide 11: Scoping Impact on Implementation- Time to adapt Survey CTO code
  Customization requires some familiarity with the SurveyCTO environment and programming techniques.
  When the selections (KPIs, tracer commodities) and adaptations have been finalized, the SurveyCTO data collection tools should be updated to reflect these decisions.
  Considering the number of changes that may need to be programmed into SurveyCTO, enough time must be set aside for the update of SurveyCTO.
  After any changes, the assessment team will need to spend some time going through the final data collection instruments to ensure that there are no remaining ‘glitches’ or ‘bugs’ in the programming, and that the questions are presented in a suitable manner.
Notes: There is usually less than a week before the end of the stakeholder/supply chain mapping workshop and the start of field work. Keeping in mind that updates to the tool can be sent out, but requires teams to be aware of this and have connectivity to download the new form. Adding additional levels does not necessarily require a new form. For example the warehousing storeroom module can be asked at an SDP or district storeroom, but time is needed to decide which form to use at which levels.

## Slide 12: Customizing Data Collection Tool (Master Questionnaire)
  The CMM survey is designed with particular scoring parameters in mind. In order to enhance comparability across time or assessments, it is not recommended that questions be removed from the CMM survey.
  • The CMM survey and the KPI data collection tool are designed to work with the data analyses templates, changes could corrupt these analyses.
  Altering questions or responses will adversely affect the interoperability of the SurveyCTO outputs and these templates.
  Limited customization may be essential such as, using the correct names for the country’s health system levels, or editing terminology or using appropriate language or terminology for the country, but these should be the only changes.
Notes: Removing questions will alter the scoring of that module.

## Slide 13: Customizing Data Collection Tool (Master Questionnaire)
  What you MUST DO:
  • Change the tracer commodities and number of months for which to collect the data.
  • Change the number of different entities and their names up to10 (e.g., Health Center, District Pharmacy, Central stores).
  • Change other facility names.
  • Add any descriptive questions.
  • Add optional KPIs selected.
  What you CANNOT do:
  • Do not remove questions from the CMM survey.
  • Do not alter CMM questions or responses.
  • Do not alter core KPIs.
Notes: Descriptive questions can be added to the CMM.
If any of the other items are altered the analysis template will not work and the survey will not be comparable over time (or across countries). Not just the number of months, but the names of those months. The cannot list is to reinforce the message from the previous slide.