## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 3: Building the Team
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Objective
Discuss key roles and responsibilities of the core assessment team
Outline key competencies of data collectors
Provide examples of team structures and recruitment strategies
Where the assessment team sits within the overall project
Core tasks of assessment team
  Examples of team structures
Key competencies of data collectors
  Examples of recruitment models
Policies, best practices, and restrictions
“Build your own team” exercise
Agenda

## Slide 3: The Big (Team) Picture
The focus of this session
Notes: Governance team:
A small governance team is needed to provide high level leadership, oversight, and decision-making. The group, which may also be known as the funders, should include at least one high-level official from key stakeholder organizations that have budget and resource authority such as the MoH, and Donor(s), depending on the local situation and needs.
Ghana: MOH, GHS, USAID, PSM
Steering Committee:
This committee directs the operational activities of the core team; it includes team members that are critical to the project and are regularly involved in operations. The steering committee should include at least one high ranking MoH official and other needed high impact stakeholders as determined by the core assessment team to ensure both that decisions carry weight, and that there is timely facilitation and approval of processes. These individuals are involved only in specific management and technical activities of the NSCA 2.0 such as informing technical decisions (e.g., scope, tracer commodities), facilitating planning, requesting and obtaining approvals, executing in-country logistics, and ensuring compliance with local protocol and appropriate channels of communication.
Ghana: MOH TWG and PSM staff

## Slide 4: Core assessment team tasks include:
Overall project management
Coordination with governance team and steering committee structure
Assessment design and survey revisions
Logistics coordination
  Routing, communication, and safety of field teams
  Central-level KI interviews
Financial management
Local recruitment
Train data collectors
Implement supply chain workshop
Data review and quality assurance management
Central-level key informant interviews (30-60 interviews, or more)
Data analysis and report writing
Dissemination of results
… what do you think?
Notes: Note to self – reference the kickoff exercise responses

## Slide 5: Mix and match: Who do you have & who do you need
Example roles
Project lead(s)
Assessment manager
Technical lead
Data manager
Data validator(s)
Logistic coordinators
Financial lead
Central-level interview team
Considerations
Cost, capacity, availability
Building buy-in and stakeholder engagement
Ensuring unbiased process and results
Staffing options
Organization staff
MOH staff or seconded government personnel
Partnering staff from other orgs or donors
Consultants
Volunteer professionals
University students

## Slide 6: Ghana example
Title | Role | Organization | LOE
Assessment Managers / Leads | Overall project and assessment leads – design, team, workshops and trainings Manage data validation and quality assurance Data analysis and report writing | GHSC-DC | 2 Specialists 50-100% / 2 months
Technical Director | Focal person for government engagement Lead stakeholder workshop and dissemination | GHSC-Ghana | 1 Director 25-50% / 3 weeks
M&E and Data Quality Specialists | Support assessment design and training Support data validation and quality assurance | GHSC-Ghana | 2 Specialists 100% / 4 weeks +
Field Logistics Coordinator | Manage daily routing of data collectors Ensure collection of all field data | GHSC-Ghana | 1 Specialist 100% / 3 weeks
Central-Level Interview Team | Interview key informants at central-level sites Manage scheduling of key informant interviews and track completion of survey modules | Consultant Junior data collector GHS officer | 2 Personnel 100% / 3 weeks 1 Person - 25% / 4 wk
Finance Lead | Manage payment of per diem and expenses Contract transportation, accommodations, etc | GHSC-Ghana, and staff support | 1 Person 33% variable, 3 weeks
Administrative | Manage workshop and trainings logistics and support other members of team | GHSC-PSM Ghana | 1 Person 100% / 2 weeks
 |  | Total | 11-person team
Governance structure: MOH, represented by TWG; USAID, funding and oversight; GHSC-PSM implementing, represented by Country Director, Technical Director, and in-country M&E Specialist
Notes: Governance structure: MOH, represented by TWG; USAID, funding and oversight; GHSC-PSM
Task: 248 sites, xxx assessments; 60 central level interviews

## Slide 7
Title | Role | Organization | LOE
Assessment Managers / Leads | Overall project and assessment leads Lead assessment design and revision Lead workshops and training Manage data validation and quality assurance Data analysis and report writing | GHSC-DC | 2 Specialists 50-100% / 2 months
Technical Director | Focal person for government engagement Lead stakeholder workshop and dissemination Support assessment design and training Interview key informants at central-level sites | GHSC-Guinea | 1 Director 100% / 3 weeks +
Field Logistics Coordinator | Manage daily routing of data collectors Ensure collection of all field data Monitor data quality process with teams | Consultant | 1 Specialist 100% / 5 weeks
Central-Level Logistics | Managed and supported key informant interviews and data collector training | GHSC-DC | 1 Personnel 100% / 2.5 weeks
Operations Lead, and support | Manage payment of per diem and expenses of 40 person-field team Contract transportation, accommodations, etc | GHSC-Guinea, and staff support | 2 Person 33% variable, 3 weeks
 |  | Total | 7-person team
Governance structure: MOH, represented by Logistics Management Unit lead advocate; USAID, funding and oversight; GHSC-PSM implementing, represented by Country Director and Technical Director
Guinea example
Notes: Governance structure: MOH, represented by TWG; USAID, funding and oversight; GHSC-PSM
Task: 248 sites, xxx assessments; 60 central level interviews

## Slide 8: Data Collectors
NSCA is a highly technical assessment - implementation requires significant health expertise, enumerator skill, professionalism and autonomy
Full NSCAs can require 40-60 (or more!) data collectors to assess all selected sites
Teams of two data collectors each travel for two weeks across the country, each conducting CMM and KPI assessments at 6-10 health facilities
All data collectors attend a full week of training prior

## Slide 9: Skills Required
Comfort with diverse supply chain functional areas (e.g. distribution, forecasting, pharmacovigilance)
Professional understanding of key health care commodities and system concepts (e.g. tracer commodities, stockout rates, LMIS tools)
Experience with large assessments and understanding of data collection and best practices
High levels of professionalism - ability to represent MoH across the country
Significant autonomy – ability to conduct assessments at multiple sites with minimal (remote) oversite
Three weeks availability – one week of training and two of data collection
Willingness to travel, including to remote areas

## Slide 10: Two approaches to recruiting data collectors
Guinea
Enumerators: Advanced-level pharmacy students and a handful of mid-level MoH officials (42 total)
Process: Individual interviews of all enumerators
Pros:
Ghana
Enumerators: Mid-level career pharmacists and supply chain experts and a handful of PSM staff (63 total)
Process: MOH invited Regional Health Directors to nominate 2-4 persons to participate in national assessment, final selections made by core assessment team

## Slide 11: Policies, best practices and restrictions
Need to use proper contractual or other mechanisms of engagements, including TORs with clearly defined qualifications, roles/responsibilities, and deliverables
Need to abide by local government statutes, regulations, and policies in developing and implementing personnel contracts and payment procedures
Explore with the MOH, stakeholders and partners to leverage their staff to promote collaboration, local ownership of the activity, and local capacity as well as to cut costs
Balance value of connections and familiarity with supply chain and the need for neutrality and presence of unbiased persons when constructing the assessment team

## Slide 12: Mix & Match Worksheet: Building your NSCA team
Notes: If have time, work through exercise together.

## Slide 13: Takeaways
Every NSCA assessment team will be unique – reflecting scope of assessment, available resources and capabilities, mix of stakeholders, and competing priorities
Minimum set of core assessment tasks need to be covered to ensure successful completion of activity
Team building and data collector recruitment processes should reflect country context, policies and statutes, team ingenuity, and universal best practices