## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 3: Data Collection Day by Day
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Objective/Outline
  Objective: To have a summary view of how all the data collection work operates during the collection period.
  Graphic- of overall operations.
  Overall data collection timeline
Notes: This slide lays out the outline of this session giving an overall picture and timelines for the process. Subsequent sessions will go into further detail.

## Slide 3: Data Collection Overview
  NSCA data collection is a very intensive exercise with significant tracking, coordination, and real-time feedback required.
  Central-level and peripheral level data collection is done simultaneously for efficiency of resources.
  Overall process is managed by a “control tower” team
Notes: This slide lays out the outline of this session giving an overall picture and timelines for the process. Subsequent sessions will go into further detail.

## Slide 4
Data Collection Operations Overview
Control Tower:
-Overall Assessment Lead(s) (1-2 people)
- Logistics Leads (2 people)
- Data Quality Team (2-4 people)
Field Teams
[20-30 teams of two enumerators each]
Central Level Teams
[1-3 teams of two enumerators (or technical staff) each]

## Slide 5: Daily Schedule Part 1
Date | Activity
Day -3 | Set up a control tower and means of communication (WhatsApp) to communicate and handle issues encountered by data collection team.
Day -2 | Practice use of control tower communication streams during data collection pilot
Day -1 | Finalize logistics and data collection plans, finish enumerator training
Day 0 (Sunday) | Deployment and pre-positioning of data collection teams
Day 1 | Data collection for sites 1 to 10 ( Data quality feedback starts)
Day 2 | Data collection for sites 11 to 20 + Central Level (Data quality feedback ongoing)
Day 3 | Data collection for sites 21 to 30 + Central Level (Data quality feedback ongoing)
Day 4 | Data collection for sites 31 to 40 + Central Level (Data quality feedback ongoing)
Day 5 | Data collection for sites 41 to 50 + Central Level (Data quality feedback ongoing)
Day 6 | Data collection teams make long distance travel to pre-position for following week
Day 7 | Rest Day
Notes: This schedule is based on 10 data collection teams. Based on the distance needed to reach the sites, some teams may need to leave earlier than the day before data collection. If training ends on a Friday. Teams will depart on Saturday or Sunday. If it is a large country teams will not return to the capital city over the weekend.

## Slide 6: Daily Schedule Part 2
Date | Activity
Day 8 | Data collection for sites 51 to 60 + Central Level (Data quality feedback ongoing)
Day 9 | Data collection for sites 61 to 70 + Central Level (Data quality feedback ongoing)
Day 10 | Data collection for sites 71 to 80 + Central Level (Data quality feedback ongoing)
Day 11 | Data collection for sites 81 to 90 + Central Level (Data quality feedback ongoing)
Day 12 | Data collection for sites 91 to 100 + Central Level (Data quality feedback ongoing)
Day 13 | Data collectors return to Capital
Day 14 | Preparation of preliminary findings reports (if needed)
Day 15 | Debrief with Donor (if applicable)
Day 16 | Debrief with MOH. Debrief with data collectors.
Day 17 | Departure
Notes: This schedule is based on 10 data collection teams. Based on the distance needed to reach the sites, some teams may need to leave earlier than the day before data collection. If training ends on a Friday. Teams will depart on Saturday or Sunday. If it is a large country teams will not return to the capital city over the weekend.